Strategy Advisory Group Meeting

Tuesday 18th September 2018, 1100hrs

Chetwynd Room, Civic Suite, 1st Floor, Stafford Borough Council

| Present Attendees | Apologies |
| --- | --- |
| Ben Hollands Camilla Denham-White Georgia Phillips Jane Kracke Jonathan Topham Lee Booth Malcolm Armstrong Naomi Bird Tim Clegg Sarah Bixter (Notes) | Interim Strategic Lead Youth Sport & Events Officer Digital / Social Media Apprentice Interim Director Senior Commissioning Mgr Public Health Workforce Manager SASSOT Board Chair Insight / Marcomms Manager Chief Executive, Stafford BC Admin Office Manager | Prof. Pauline Walsh Prof. Derek Peters Alistair Fisher Kimiyo Rickett |

Summary of Actions

| No. |  |
| --- | --- |
| 1. | Apologies – as above Welcome by Malcolm Armstrong Introductions by everyone Decision made that Ben Hollands, Interim Strategic Lead, will take the lead with this work and act as the PMIF Administrator |
| 2. | Notes of last meeting – N/A as first meeting |
| 3. | Overview of PMIF Process – Ben Hollands |
| 4. | Optional Modules Link to Quest Modules There are 5 competency modules which every CSP will be measured against We can then choose to either: Work towards the 5 competency modules only or Choose up to 3 additional modules Discussion around the suitability of choosing additional modules considering where we are as an organisation, the time constraints and the interim leadership Decision made to concentrate our time and effort on the 5 competency modules with a view to looking at picking up additional modules later in the process. |

| No. |  |
| --- | --- |
| 5. | Partner Satisfaction Survey Discussion around if any additional questions were required. Naomi to look at the Quest Module on Partnerships and check if anything further needs asking This year it’s more about quality of participants over the quantity. Last year we sent it to180 this year is more likely to be 40-50. Ideally we need contacts from a local and possibly Regional Level not a National Level to take part Naomi to send the distribution list for review in the next Governance & Advisory Group meeting. They can provide feedback and insight for future use. Action Points 1 & 2 |
| Actions | Owner | Date |
| Naomi to look at the Quest Module on Partnerships and check if anything further needs asking | Naomi Bird | 21.09.18 |
| Naomi to send the distribution list for review in the next Governance & Advisory Group meeting. They can provide feedback and insight for future use. | Naomi Bird | 09.10.18 |
| 6. | Self-Assessment Process, Improvement Plan & Strategic Outcomes Self-Assessment from September onwards on the 5 competency modules to be carried out identifying evidence. Documentation to be completed by end of November to ensure time for tweaking. Discussion around the importance of a rounded view and varied insight. Board members, core team and partners to be invited to participate. External Assessment to be completed externally between October and January. CSP’s can suggest dates for assessment but they are not guaranteed. Dates put forward by SASSOT are (in order of preference): 17-18 December 2018 13-14 December 2018 10-11 January 2019 Improvement Plan - We are still awaiting guidance on the Improvement Plan and whether or not there will be a template and/or what the requirements/expectations will be. |
| 7. | Process Governance & Next Steps Discussion around how best to manager the process and our next steps Agreed that a small working group will meet next Wednesday 26th to analyse each module and produce an action plan for each module. Discussion around partners being involved in the assessment process. Colleagues to look at each module and suggest suitable partners to be involved and email Ben with suggestions. Group to meet again at 10am on 13th November 2018. Action Points 3, 4 & 5 |
| Actions | Owner | Date |
| Small working group to meet on Wednesday 26th September. Invite to be sent out and room booked. | Sarah Bixter | 21.09.18 |
| Colleagues to look at each module and suggest suitable partners to be involved and email Ben with suggestions. | All | 26.09.18 |
| Group to meet again at 10am on 13th November 2018. Invite to be sent out and room booked. | Sarah Bixter | 21.09.18 |
| 8. | AOB - None |
| 9. | Date of next meeting(s) Tue 13th November 2018, 9.30am, Walton Room, Stafford Borough Council |

| Actions | Owner | Date |
| --- | --- | --- |
| Naomi to look at the Quest Module on Partnerships and check if anything further needs asking | Naomi Bird | 21.09.18 |
| Naomi to send the distribution list for review in the next Governance & Advisory Group meeting. They can provide feedback and insight for future use. | Naomi Bird | 09.10.18 |
| Small working group to meet on Wednesday 26th September. Invite to be sent out and room booked. | Sarah Bixter | 21.09.18 |
| Colleagues to look at each module and suggest suitable partners to be involved and email Ben with suggestions. | All | 26.09.18 |
| Group to meet again at 10am on 13th November 2018. Invite to be sent out and room booked. | Sarah Bixter | 21.09.18 |